# What We Delivered — October 2026 (Month 5)

Project: Texas Cool Schools — Rio Grande Valley (Grant #25065)
From: UTRGV Agroecology Lab (Dr. Engil Pereira & Donald R. Reed III)
To: Texas Trees Foundation (Jorge Rodriguez, Project Liaison; Kristinaoshia Torres, Project Manager)
Date: October 29, 2026
Total Billed This Month: $6,272.00 (Invoice #5)

## Here is a plain-language summary of what the UTRGV team completed and delivered this month:

Streamlined Public & Student-Friendly Dashboard v2 (Deliverable C — $3,730.00): In direct response to the Texas Trees Foundation v1 design review, we simplified the top navigation bar from 19 tabs down to 8 core public tabs plus 3 interactive student learning labs. Six secondary technical tabs (Site Zoning, Economic/ROI, Trails, Wind, Water, and Soil) were removed from the public navigation while preserving the full 49-page v1 engineering suite on a dedicated Git archive branch (archive/v1-full-suite).

Consolidated Heat & Shade Tab with Representative Campus Simulations: We consolidated Surface Breakdown, the 3D Shade Model, and Temperature under the Albedo & Reflectance page (albedo.html) and built one-click representative campus simulations for J.W. Caceres Discovery Intermediate (Donna ISD) and Ruben Hinojosa Elementary (Mercedes ISD).

Before Planting → Newly Planted (Year 1) → Grown Trees (10–15 Yr) Impact Reports: We added 3-stage comparison reports across all retained modeling pages (Dashboard Overview, Canopy Over Time, Albedo & Reflectance, Impact, and i-Tree Eco Ledger) so stakeholders can compare initial planting against mature 10–15 year tree benefits.

Realistic Schoolyard Soil Calibration in the Backend: We calibrated our 10–15 year tree canopy and ecosystem projections to automatically account for compacted semi-urban schoolyard soils in the backend (projecting realistic 10–15 year canopy of ~22.8% for Donna ISD and ~21.6% for Mercedes ISD) while hiding technical soil mechanics formulas from students and the general public.

Live District Upload Feeds & Interactive Student Labs: We preserved Biodiversity and the Tree Sponsorship Roster as live district-updated modules (exempt from static Pre/Post snapshots) and linked three interactive elementary/middle school labs in the top navigation bar: the Birding & Tree Bulletin Board (Parts of a Cowboy & Chachalaca & Friends), the Tree Stewardship Journal, and the IR Surface Temp Lab.

2027 Reporting Workplan & Final Baseline Atlas Lock (Deliverable A — $2,542.00): We prepared the formal 2027 Reporting Workplan defining quarterly review cycles, UTRGV vs. TTFS vs. ISD roles, and the Spring/Fall 2027 teacher and facilities training schedule, and completed the October 31 final baseline lock for the Pre-Planting Environmental Atlas across all 8 campuses.

## Summary of October 2026 Deliverables & Links

| Milestone ID | Contract Deliverable | Key Artifacts / Live Links | Amount |
| --- | --- | --- | --- |
| oct-26-1 (Deliverable C) | Dashboard v2 near-final; ingestion & styling docs updated | Streamlined v2 Dashboard (sunaxle.github.io/ttfs-cool-schools-dashboard/) Month 5 Progress Report (docs/Month_5_Progress_Report.md) | $3,730.00 |
| oct-26-2 (Deliverable A) | Prep 2027 reporting workplan (review cycles, roles) & Baseline Lock | 2027 Reporting Workplan (docs/2027_Reporting_Workplan.md) | $2,542.00 |
| TOTAL | October 2026 (Month 5 — Invoice #5) | Cumulative Billed: $97,335.00 / $157,625.00 (61.8%) | $6,272.00 |