# Monthly Progress Report — Month 5 (October 2026)

Project Title: Texas Cool Schools — Rio Grande Valley (Grant #25065)
Subaward Agreement: Master Service Agreement TTF_UTRGV_FINAL_05252026
Reporting Period: October 1, 2026 – October 31, 2026 (Month 5 of 19)
Date Submitted: October 29, 2026
Prepared By: Dr. Engil Pereira (PI) & Donald R. Reed III (Graduate Research Assistant), UTRGV School of Earth, Environmental, and Marine Sciences (SEEMS)
Submitted To: Jorge Rodriguez (Project Liaison & Site Lead, Operations) & Kristinaoshia Torres (Project Manager), Texas Trees Foundation (TTFS)

## 1. Executive Summary

During October 2026 (Month 5), the UTRGV Agroecology Lab team completed the two scheduled contractual milestones under Exhibit D of the Master Service Agreement: (1) Deliverable C (oct-26-1: $3,730.00): Near-final deployment of Dashboard v2 incorporating the Texas Trees Foundation v1 design review feedback, navigation streamlining, consolidated heat/shade campus simulations, 3-stage Pre/Post-to-Mature impact reports, backend semi-urban soil growth calibration, and interactive student learning labs; and (2) Deliverable A (oct-26-2: $2,542.00): Preparation of the formal 2027 Reporting Workplan (review cycles, stakeholder roles, and training schedule) and execution of the October 31 Final Baseline Atlas Lock across all 8 participating campuses in Donna ISD and Mercedes ISD.

## 2. Milestone Completion & Technical Accomplishments

### 2.1 Deliverable C (oct-26-1): Dashboard v2 Near-Final & UX Streamlining ($3,730.00)

Navigation Streamlining & Full v1 Archive Preservation: Removed 6 secondary technical tabs (Site Zoning, Economic/ROI, Trails, Wind, Water, Soil) from the primary navigation bar to create a focused, public- and student-friendly interface while preserving the complete 49-page v1 engineering suite on Git branch archive/v1-full-suite (tag v1.0-full-archive).

Consolidation of Heat & Shade Modules with Representative Campus Simulations: Consolidated Surface Breakdown, the 3D Shade Model, and Temperature under Albedo & Reflectance (albedo.html) with one-click representative campus simulations for J.W. Caceres Discovery Intermediate (Donna ISD) and Ruben Hinojosa Elementary (Mercedes ISD).

3-Stage Pre/Post-to-Mature Impact Reports: Added Before Planting → Newly Planted (Year 1) → Grown Trees (10–15 Yr) impact comparison cards across Dashboard Overview (dashboard_map.html), Canopy Over Time (canopy.html), Albedo & Reflectance (albedo.html), Impact (index.html), and i-Tree Eco Ledger (itree_ledger.html).

Backend Semi-Urban Schoolyard Soil Calibration: Calibrated the i-Tree Eco and canopy growth engine (config.js, itree_engine.js) to automatically apply compacted semi-urban schoolyard soil parameters in the backend (0.64x radial growth rate, 0.84x max crown radius, 2-year establishment lag, 94% survival), projecting realistic 10–15 year canopy coverage of ~22.8% (Donna ISD) and ~21.6% (Mercedes ISD) without exposing complex soil mechanics equations to students or the public.

Live District Feeds & Tactile Elementary/Middle School Labs: Maintained Biodiversity (biodiversity.html) and Tree Sponsorship Roster (rivas_tree_roster.html) as live district-updated modules, and integrated three COPPA/FERPA-compliant student labs into the navigation bar: Birding & Tree Bulletin Board (birding_biodiversity_bulletin.html), Tree Stewardship Journal (tree_stewardship_journal.html), and IR Surface Temp Lab (ir_surface_temp_lab.html).

Active Review Badges & Page-Level Alignment Roadmaps: Added visual Under Construction navigation badges and page-top alignment banners outlining the November–December 2026 consolidation roadmap across pages undergoing district feedback review.

### 2.2 Deliverable A (oct-26-2): 2027 Reporting Workplan & Final Baseline Lock ($2,542.00)

2027 Reporting Workplan (docs/2027_Reporting_Workplan.md): Authored the comprehensive 2027 operational workplan establishing the quarterly data ingestion and review cycles (Q1–Q4 2027), the 10-business-day TTFS/UTRGV review SLA, RACI responsibilities across UTRGV, TTFS, and ISD liaisons, and the 2027 educator/facilities training calendar.

Final Pre-Planting Baseline Atlas Lock: Completed final quality assurance and immutable baseline locking of the 2026 pre-planting environmental dataset across all 8 Donna ISD and Mercedes ISD campuses ahead of the Fall 2026 / Winter 2027 planting window.

## 3. Financial & Budget Summary (Month 5 — October 2026)

| Deliverable Category | Total Contract Budget | Prior Billed (Months 1–4) | Current Period (Month 5) | Cumulative Billed | Remaining Balance |
| --- | --- | --- | --- | --- | --- |
| Deliverable A: Pre- & Post-Planting Data & Reports | $52,542.00 | $27,730.00 | $2,542.00 | $30,272.00 | $22,270.00 |
| Deliverable B: Monitoring Docs & Training Workshops | $52,541.00 | $29,521.00 | $0.00 | $29,521.00 | $23,020.00 |
| Deliverable C: Interactive Geospatial Dashboard | $52,542.00 | $33,812.00 | $3,730.00 | $37,542.00 | $15,000.00 |
| TOTAL CONTRACT (Grant #25065) | $157,625.00 | $91,063.00 (57.8%) | $6,272.00 | $97,335.00 (61.8%) | $60,290.00 (38.2%) |

## 4. Upcoming Milestones — Month 6 (November 2026)

nov-26-1 (Deliverable C — $3,730.00): Model consolidation, alignment of visuals with text, and figure index build across retained v2 pages.

nov-26-2 (Deliverable B — $2,541.00): Training #1 preparation finalized and workshop logistics confirmed with Donna ISD and Mercedes ISD.

nov-26-3 (Deliverable A — $2,542.00): Collect and integrate TTFS and school district partner feedback on the 2027 Reporting Workplan and TEKS lesson modules.