June DESCRIPTIONS

A. Environmental Baseline Data Summary

Kickoff activities completed and participating campus list confirmed.

Dashboard views (v.1) established for all participating Donna ISD & Mercedes ISD campuses.

Campus geographic boundaries and deployment locations established.

Remote-sensing baseline framework and climate indicator modules developed.

B. Environmental Monitoring Documentation Package

Data Dictionary developed (75%).

Monitoring SOP framework developed (75%).

Environmental monitoring database schema established.

Digital monitoring documentation integrated into Dashboard (v1).

C. Forecasting & Digital Dashboard Support Materials

Dashboard (v.1) scaffolding and architecture developed.

CSV and GeoJSON ingestion prototype implemented.

Heat-surface visualization framework established.

Dashboard feature development and model testing initiated.

D. Environmental Data Collection Training & Technical Assistance

No June milestone allocation for this reporting period.

June meeting attendance: June 17, June 25

July DESCRIPTIONS

A. Environmental Baseline Data Summary

Completed final QA review of baseline environmental datasets and campus information structure.

Finalized Version 1 baseline tables and campus fact sheets for participating campuses.

Verified campus boundaries, deployment locations, and environmental indicator layers.

Refined baseline resources supporting future canopy growth and environmental impact tracking.

B. Environmental Monitoring Documentation Package

Advanced Environmental Monitoring Documentation Package to Version 0.8 for internal review.

Continued development of the data dictionary, metadata standards, and monitoring procedures.

Expanded SOPs for field documentation, photography, and quality assurance workflows. Participated in Photography SOP Walk-Through Training on July 14.

Integrated lessons learned from dashboard development into monitoring documentation.

C. Forecasting & Digital Dashboard Support Materials

Continued Dashboard Version 1 for refinement, testing, and feature development.

Developed and tested tree inventory, canopy growth, and shade projection modules.

Enhanced GIS mapping tools for campus boundaries, land-cover classification, and spatial analysis.

Refined heat, cooling, solar radiation, and environmental visualization modules.

Tested dashboard architecture, data-ingestion workflows, and user interface components.

Compiled user notes and drafted Training #1 outline for future stakeholder onboarding.

Submitted three weekly blog posts to support project alignment, stakeholder communication, and continued project discovery efforts.

D. Environmental Data Collection Training & Technical Assistance

Participated in Photography SOP Walk-Through Training on July 14.

Provided technical assistance regarding photo documentation standards and monitoring workflows.

Reviewed requirements for integrating field documentation into project reporting processes.

July: Beginning the review of submitted tree canopy collections, community photos and CAD designs. 4 team meeting check ins conducted. Standing weekly team meetings.

August DESCRIPTIONS

A. Environmental Baseline Data Summary

Digitized multi-campus GIS surface zoning and parcel boundaries across participating Donna ISD and Mercedes ISD pilot campuses.

Finalized and locked Version 1 campus surface-area breakdown fact sheets and area tables (e.g., M. Rivas Primary / J.W. Caceres Discovery Academy: 885,925 sq ft).

Implemented automated geometric QA/QC topology validation (Turf.js) for polygon consistency, area calculations, and spatial layer integrity.

Verified GIS layer alignment against Studio Outside landscape architectural CAD drawings and high-resolution aerial imagery.

B. Environmental Monitoring Documentation Package

Advanced Training Materials package to Version 0.5, creating structured training models for school administrators and lead science teachers.

Developed comprehensive Educator Outdoor Lab Handout ("The Great Campus Shade Hunt") for teachers to implement heat/canopy monitoring with students.

Established and deployed the formal Technical Assistance (TA) Log schema adhering to Texas A&M Forest Service (TFS) grant compliance standards.

Maintained and updated field monitoring Standard Operating Procedures (SOP v0.6) for tree caliper (DBH), canopy radius, and FLIR thermal verification.

Integrated digital monitoring documentation and protocol references directly into the interactive dashboard doc viewer.

C. Forecasting & Digital Dashboard Support Materials

Compiled the Environmental Modeling Visuals & Figure Package documenting diurnal surface heat dynamics (9 AM, 1 PM peak, 5 PM) and 5/10-year longitudinal canopy growth projections.

Authored the Dashboard v2 Architectural Planning Memo outlining stakeholder feedback, PWA offline field caching, and modular integration roadmap.

Deployed Dashboard v1.2 featuring an organized 3-tier navigation bar cleanly categorizing Grant Deliverables, Bonus Simulations, and Admin Portals.

Developed and deployed four core prototype portals: Role-Based Access Control (RBAC), Campus Tree Sponsorship/Donors, Child-Friendly Habitat Spotter, and Password-Protected TEKS Lesson Plans.

Integrated dynamic Solar Shade Geometry Lab, 3D canopy orbit rendering, and the USDA i-Tree Eco-Services calculation engine.

Added dynamic 158 Tree Species Growth Registry table, FLIR infrared heat transfer layers, and automated surface area calculation widgets.

Hardened frontend architecture across 49 static pages: 100% extraction of embedded styles and scripts into dedicated .css and .js files, strict IIFE scoping, semantic ARIA accessibility, CDN preconnecting, and lazy asset loading.

Configured automated GitHub Pages CI/CD deployment pipeline and production build workflows.

D. Environmental Data Collection Training & Technical Assistance

Developed two specialized training models: (1) Administrator Training Slide Deck on heat, climate, and Average Daily Attendance (ADA) funding; (2) Teacher & Student Outdoor Lab investigation guide for microclimate data collection.

Completed Training Session Facilitator Guide detailing session execution, participant objectives, and field equipment setup.

Established formal Technical Assistance logging workflows for district support inquiries and response tracking.

Provided technical guidance on field documentation standards, photo logging, and grant reporting integration.

August: Standing weekly team check-ins conducted throughout August. Ongoing collaborative review of campus CAD drawings, GIS zoning datasets, field measurement protocols, and dashboard deliverables with Texas Trees Foundation and UTRGV evaluation team.