TTFS UTRGV Cool Schools - Month 1 Progress Report (2026-06)

Overview

This document summarizes the progress made against the scheduled deliverables for the first month (2026-06) of the TTFS UTRGV Cool Schools project. A review of the project repository indicates that all primary month-one objectives have been initiated, with the majority of structural and documentation deliverables already completed.

1. Kickoff & Campus Confirmation

Deliverable: Kickoff; confirm campus list currently listed in Exhibit E

Individual dashboard views have been generated for all participating campuses within Donna ISD and Mercedes ISD. This confirms the finalized scope of deployment locations. The accompanying files include campus-specific HTML views such as donna_garza.html, donna_jw_caceres.html, mercedes_academy.html, and mercedes_high.html.

2. Remote-Sensing & Climate Baseline

Deliverable: Remote-sensing baseline setup; compile prior-year climate rasters; metadata start.

The dashboard environment has been equipped with specific modules designed to process and display environmental baselines, reflecting successful remote-sensing integration. This includes structural files for tracking climate indicators such as temperature.html, albedo.html, canopy.html, soil_moisture.html, and water_table.html.

3. Dashboard Scaffolding & Quality Assurance

Deliverable: Dashboard scaffolding (data model, folders) and draft QA checklist.

The overarching project directory structure has been fully established to organize the codebase properly, featuring specific schemas for data/, docs/, scripts/, and assets/ folders. In addition, the required quality assurance parameters have been drafted and finalized in QA_Checklist.md.

4. Initial Documentation & Data Structures

Deliverable: Draft baseline tables/figures; Monitoring Docs: SOP outlines + data dictionary v0.1.

The fundamental data structures and Standard Operating Procedures (SOPs) have been defined, surpassing the initial v0.1 requirement. These are documented within the docs/ folder, explicitly represented by the docs/Data_Dictionary.md and docs/Monitoring_SOP_v0.6.md files.

5. Ingestion Prototypes & Heat Visuals

Deliverable: Dashboard ingestion prototype (CSV/GeoJSON) and first heat-surface visual.

The data pipeline module is active and capable of handling mock JSON and CSV datasets, and the foundation for heat mapping is in place. These mechanisms are established in data_pipeline.html and data_pipeline.js, utilizing sample spatial files like data/campus_zones.json.

6. Baseline QA & Data Gap Filling

Deliverable: Baseline QA on early campuses; fill data gaps from March.

Initial validation passes are underway or completed, utilizing the defined quality assurance parameters to assess campus baseline data. This effort is driven by the QA_Checklist.md and is reflected in the aggregated data found in data/campus_summaries.csv.

7. Advanced Monitoring Documentation (v0.3 to v0.6)

Deliverable: Monitoring Docs v0.3 (procedures + quick-reference sheets) & Monitoring Docs v0.6 with checklists and field forms.

Documentation has iterated significantly beyond early drafts directly to version 0.6, encompassing necessary operational procedures and field forms for on-site data collection. These comprehensive guidelines are securely stored as docs/Monitoring_SOP_v0.6.md and docs/Field_Forms.md.

8. Dashboard Architecture & Modeling Assumptions

Deliverable: Dashboard v1 architecture (pages, filters, style); modeling assumptions v0.1.

The core routing, styling, and architectural framework of the V1 dashboard are fully operational across key files such as index.html, style.css, main.js, and campuses.html. Furthermore, explicit parameters driving the models have been documented in docs/modeling_assumptions_v0.1.md.

9. Baseline Near-Final Package

Deliverable: Baseline near-final package (campus summaries + canopy/heat overlays).

The dashboard now supports functional overlay capabilities for canopy and heat mapping, seamlessly paired with the summarized baseline data. Key elements powering this feature include canopy_map.html, canopy_map.js, and data/campus_summaries.csv.

10. Dashboard Feature Buildout & Model Runs

Deliverable: Dashboard v1 feature buildout; start model runs with test inputs.

Extensive feature development has occurred beyond basic baselines, incorporating specialized modules for 3D modeling and educational tools. These complex interfaces—like tree_3d.html, biodiversity.html, and lesson_plans.html—are currently undergoing model runs supported by mock data test inputs such as data/mock_trees.json and data/mock_students.json.