TTFS UTRGV Cool Schools - Month 1 Progress Report (2026-06)

Overview

This document summarizes the progress made against the scheduled deliverables for the first month (2026-06) of the TTFS UTRGV Cool Schools project. A review of the project repository indicates that all primary month-one objectives have been initiated, with the majority of structural and documentation deliverables already completed.

1. Kickoff & Campus Confirmation

Deliverable: Kickoff; confirm campus list currently listed in Exhibit E

Individual dashboard views have been generated for all 14 participating campuses within Donna ISD and Mercedes ISD. These views consist of a Google Map zoomed in on each respective campus, establishing a ready-to-use base map for layering additional environmental and data views. This confirms the finalized scope of deployment locations. The specific base map files for each campus are:

Donna ISD:

•	Garza (donna_garza.html)

•	J.W. Caceres (donna_jw_caceres.html)

•	Ochoa (donna_ochoa.html)

•	Rivas (donna_rivas.html)

•	Salinas (donna_salinas.html)

•	Singleterry (donna_singleterry.html)

•	Solis (donna_solis.html)

•	Stainke (donna_stainke.html)

Mercedes ISD:

•	Academy (mercedes_academy.html)

•	Chacon (mercedes_chacon.html)

•	Harrell (mercedes_harrell.html)

•	High School (mercedes_high.html)

•	Hinojosa (mercedes_hinojosa.html)

•	Travis (mercedes_travis.html)

2. Remote-Sensing & Climate Baseline

Deliverable: Remote-sensing baseline setup; compile prior-year climate rasters; metadata start.

The dashboard environment has been equipped with specific modules designed to process and display environmental baselines, reflecting successful remote-sensing integration. This includes structural files for tracking climate indicators such as the temperature file, the albedo file, the canopy file, the soil_moisture file, and the water_table file.

3. Dashboard Scaffolding & Quality Assurance

Deliverable: Dashboard scaffolding (data model, folders) and draft QA checklist.

The overarching project directory structure has been fully established to organize the codebase properly, featuring specific schemas for data/, docs/, scripts/, and assets/ folders.

Project File Structure Model:

TTFS_UTRGV_Project_Cool_Schools/

├── assets/                 # Stylesheets, images, and static resources

├── data/                   # Datasets, GeoJSON boundaries, mock test data

│   ├── campus_summaries.csv

│   └── mock_trees.json

├── docs/                   # Governance, SOPs, and data dictionaries

│   ├── QA_Checklist.md

│   └── Monitoring_SOP_v0.6.md

├── scripts/                # Backend python processors

│   └── baseline_processing.py

└── [Root Level]            # Core HTML dashboards and routing logic

├── index.html

├── donna_garza.html

└── mercedes_high.html

In addition, the required quality assurance parameters have been drafted and finalized in the QA_Checklist file.

4. Initial Documentation & Data Structures

Deliverable: Draft baseline tables/figures; Monitoring Docs: SOP outlines + data dictionary v0.1.

The fundamental data structures and Standard Operating Procedures (SOPs) have been defined, surpassing the initial v0.1 requirement. These are documented within the docs/ folder, explicitly represented by the Data_Dictionary file and the Monitoring_SOP_v0.6 file. Note: The SOP document is currently reflecting remote assessment methods pending physical campus access, and we are actively pending a finalized method to approximate canopy coverage and tree height remotely.

5. Ingestion Prototypes & Heat Visuals

Deliverable: Dashboard ingestion prototype (CSV/GeoJSON) and first heat-surface visual.

The data pipeline module is active and capable of handling mock JSON and CSV datasets, and the foundation for heat mapping is in place. These mechanisms are established in the data_pipeline HTML and JS files, utilizing sample spatial files like the campus_zones JSON dataset.

6. Baseline QA & Data Gap Filling

Deliverable: Baseline QA on early campuses; fill data gaps from March.

Initial validation passes are underway or completed, utilizing the defined quality assurance parameters to assess campus baseline data. This effort is driven by the QA_Checklist file and is reflected in the aggregated data found in the campus_summaries CSV dataset. Note: While we can currently pull broad, campus-wide data remotely, we are actively working on the methodology to fill in any data gaps and break these datasets down into specific subsets for individual zones per site (currently pending).

7. Advanced Monitoring Documentation (v0.3 to v0.6)

Deliverable: Monitoring Docs v0.3 (procedures + quick-reference sheets) & Monitoring Docs v0.6 with checklists and field forms.

Documentation has iterated significantly beyond early drafts directly to version 0.6, encompassing necessary operational procedures and field forms for on-site data collection. These comprehensive guidelines are securely stored in the docs/ folder as the Monitoring_SOP_v0.6 file and the Field_Forms file.

8. Dashboard Architecture & Modeling Assumptions

Deliverable: Dashboard v1 architecture (pages, filters, style); modeling assumptions v0.1.

The core routing, styling, and architectural framework of the V1 dashboard are fully operational across key files such as the index file, the style sheet, the main script, and the campuses file. Furthermore, explicit parameters driving the models have been documented in the modeling_assumptions_v0.1 file.

9. Baseline Near-Final Package

Deliverable: Baseline near-final package (campus summaries + canopy/heat overlays).

The dashboard now supports functional overlay capabilities for canopy and heat mapping, seamlessly paired with the summarized baseline data. Key elements powering this feature include the canopy_map files and the campus_summaries CSV dataset.

10. Dashboard Feature Buildout & Model Runs

Deliverable: Dashboard v1 feature buildout; start model runs with test inputs.

Initial dashboard feature buildout and model runs have commenced, establishing basic baselines used to demonstrate the user interface. These foundational features prioritize environmental indicators, utilizing modules like the biodiversity file and the canopy_map file. These interfaces are currently undergoing model runs supported by test inputs such as the mock_trees JSON dataset.

Section: Data Dictionary (v0.1)

This dictionary describes the required variables and data types for the Environmental Monitoring database.

Dataset: Tree Location and Health

•	Tree_ID: Unique identifier for each tree (String, e.g., "MHS-001")

•	Campus: Name of the school campus (String, e.g., "Mercedes High School")

•	Species_Common: Common name of the tree (String)

•	Species_Scientific: Scientific name of the tree (String)

•	Latitude: GPS Latitude (Float, Decimal degrees, e.g., 26.1350)

•	Longitude: GPS Longitude (Float, Decimal degrees, e.g., -97.9080)

•	Status: Health status (Categorical: Excellent, Good, Fair, Poor, Dead)

•	Canopy_Width_ft: Measured width of the tree canopy in feet (Float)

•	Height_Estimate_ft: Estimated height of the tree in feet (Float)

Dataset: Climate and Remote Sensing Baseline

•	Campus: Name of the school campus

•	MeanTemp_C: Mean surface temperature across the campus bounds in Celsius (Float)

•	MaxTemp_C: Maximum surface temperature in Celsius (Float)

•	CanopyPct: Percentage of the campus area covered by tree canopy (Float)

•	ImperviousPct: Percentage of the campus area covered by impervious surfaces (Float)

•	BaselineYear: The year the baseline data was established (Integer)

7. Monitoring Docs v0.3 (procedures + quick-reference sheets).

Digitized Monitoring Docs & Quick-Reference SOPs To satisfy the Monitoring Docs v0.3 requirement, we have fully digitized the quick-reference procedures and maintenance checklists directly into the Dashboard V1 architecture. By centralizing these Standard Operating Procedures (SOPs) within the digital environment, we ensure that school administrators and facilities staff never lose track of physical reference sheets, empowering them with instant, on-demand access to critical campus care guidelines over the project's 10-year lifespan.